## Josh
Date | User Story | Hours | Description
2025-09-23 | NA | 0.75 | Obtained intial Project 2 code. Set up project 2 forked repository, and examined the initial code base.
2025-09-23 | NA | 1 | Met with team to discuss Project 2, details of the code, and initial user story estimates.
2025-09-25 | 6 | 0.5 | Worked on the UI to add buttons for interactive and automatic mode.
2025-09-25 | 5 | 0.5 | Applied minor tweaks to Gavin's AI class to make further extension easier. Added buttons for AI difficulty.
2025-09-26 | NA | 0.25 | Met with GTA to discuss project 2.
2025-09-29 | 5 | 0.25 | Fixed a bug with our AI play that would leave the starting screen buttons still accessible. Bug was most prominent in Auto-mode.
2025-09-29 | 1 | 0.25 | Current version of interactive mode no longer allowed replayability after fixing above bug, so modified the player-alternation code to compensate.
2025-09-29 | 2 | 0.25 | Experimented with refactoring the easy mode function to eliminate redundancies. Used this function as the proof of concept for my optimizations.
2025-09-29 | 3 | 0.125 | Applied reductions to medium mode function.
2025-09-29 | 4 | 0.125 | Applied reductions to hard mode function.
2025-09-29 | NA | 2.17 | Assigned reference user stories to each Project 2 user story in the estimates document. Calculated time estimates from the story point values. Resolved an upload issue in the GitHub repository.
2025-09-30 | 5 | 0.75 | Spent this time investigating and fixing a problem with user input handling, which enabled the user to interfere with the automatic AI's gameplay.
2025-09-30 | 8 | 0.25 | Applied minor timing changes throughout the code so that the sound effects would be on time to a better degree.
2025-09-30 | NA | 1 | Drafted an updated UML class diagram. Used Team 5's project 1 diagram as a base, then added the AISolver class and updated the PlayScreen, App, and VictoryScreen classes, which we added attributes to.
2025-10-03 | NA | 1.5 | Defined the basic structure of the System Architecture document. Added the introduction, components, and data flow discussions.
2025-10-03 | NA | 0.5 | Final demo with GTA

## Gavin
Date | User Story | Hours | Description
2025-09-23 | NA | 1 | Met with team to discuss Project 2, details of the code, and initial user story estimates.
2025-09-24 | 1 | 1 | Partially defined AiSolver class
2025-09-24 | 2 | 1 | Implemented features for automatic, easy mode.
2025-09-26 | 1 | 0.5 | Further defined AISolver class and further integrated the class into previous groups code.
2025-09-26 | 4 | 1 | Implemented automatic hard mode.
2025-09-26 | 1 | 1.5 | Implemented interactive AI mode.
2025-09-26 | NA | 0.5 | Added comments to some coding sections.
2025-09-26 | NA | 0.25 | Met with GTA to discuss project 2.
2025-09-29 | 1 | 0.5 | Further defined AISolver class
2025-09-29 | 3 | 1.5 | Implemented medium mode for AI. Game keeps track of winner/loser
2025-10-03 | NA | 0.5 | Final testing and misc. code cleanup.
2025-10-03 | NA | 0.5 | Final demo with GTA

## Mark
Date | User Story | Hours | Description
2025-09-23 | NA | 1 | Met with team to discuss Project 2, details of the code, and initial user story estimates.
2025-09-26 | NA | 0.25 | Met with GTA to discuss project 2.
2025-09-30 | 7 | 2 | Added timer to display on victory screen
10/02/2025NA | NA | 2 | Added comments, enhanced timer display functionality, reviewed documentation
2025-10-03 | NA | 0.5 | Tested code before demo
2025-10-03 | NA | 0.5 | Final demo with GTA

## Bisshoy
Date | User Story | Hours | Description
2025-09-26 | NA | 0.25 | Met with GTA to discuss project 2.
2025-09-29 | 8 | 1.5 | Added sound effects on clicking, flagging, and clicking on a bomb
2025-09-29 | 8 | 0.5 | Added sound button that can be toggled on/off on the menu screen
2025-09-30 | NA | 0.5 | Met up with team to go over the project and assigning duties
2025-10-01 | NA | 1 | Added additional comments on the codes and general cleaning up
2025-10-03 | NA | 0.5 | Final demo with GTA

## Max
Date | User Story | Hours | Description
2025-09-23 | NA | 1 | Met with team to discuss Project 2, details of the code, and initial user story estimates.
2025-09-25 | NA | 2 | Reviewing code base
2025-09-26 | NA | 0.25 | Met with GTA to discuss project 2.
2025-09-30 | DROPPED | 1 | Implementing screen for leaderboard
2025-10-01 | DROPPED | 2 | implementing list display | DROPPED = User story that was cut due to time constraints.
2025-10-02 | DROPPED | 5 | File I/O, refactoring, and bug fixes
2025-10-03 | DROPPED | 0.5 | Bug fixes
2025-10-03 | NA | 0.5 | Final demo with GTA